## Proposed Winter Notices
ID | Location | Region | Affected Waterway | Description | Start Date | End Date | Upstream winding hole | Downstream winding hole
3023 | Bridge 205, Mill Lift Bridge | South-East | Oxford Canal | Our contractor will be automating the lift bridge with a towpath side pedestal. Please note, road access across the bridge should not be affected by these works. | 04-01-2016 | 29-01-2016 | Winding Hole, Somerton (65m downstream from Bridge 196, Somerton Bridge) | Heyford Wharf Turning (60m upstream from Bridge 206, Heyford Wharf Bridge)
3025 | Bridge 62, West Mills Swingbrdge | Kennet and Avon | Kennet & Avon Canal | Our Contractor will be installing drop arm barriers including a new user pedestal, a major service to the hydraulic system, and a new control panel. Please note, road access across the bridge should not be affected by these works. | 25-01-2016 | 04-03-2016 | Dreweatt's 55 Foot Winding Hole (30m downstream from Dreweatt's Bridge) | Winding Hole, West Mills (60m downstream from Bridge 62, West Mills Swingbrdge)
3027 | Bridge 21, Norton Green Drawbridge | Central Shires | Caldon Canal | Our contractor will be automating the drawbridge with powerpack and pedestal. | 08-02-2016 | 26-02-2016 | Winding Hole, Hazelhurst (30m upstream of Bridge 33, Brick Kiln Bridge) | Winding Hole, Foxley (345m upstream from Bridge 16A, Factory Access Bridge)
3029 | Islington Tunnel | London | Regent's Canal | Our engineers will undertaking a Principal Inspection of Islington Tunnel. This will require at least two passes through the Tunnel with an inspection craft. Boaters may be asked to wait whilst our boat is in the Tunnel but will be allowed through at the end of each pass. | 08-12-2015 | 08-12-2015 | Adjacent to Battlebridge Basin. | Adjacent to City Road Basin.
3031 | Bath No.1 Tunnel and Bath No.2 Tunnel | Kennet and Avon | Kennet & Avon Canal | Our engineers will undertaking a Principal Inspection of Bath No.1 Tunnel and Bath No.2 Tunnel. The navigation will be closed between the tunnels. | 15-12-2015 | 15-12-2015 | Adjacent to Darlington Wharf. | Adjacent to Bathwick Hill Bridge.
3033 | River Crane Aqueduct, Hayes, London, Grand Union Canal | London | Grand Union Canal | Repairs to brickwork. | 04-01-2016 | 11-03-2016 | Junction of Grand Union main line and the Slough arm | Junction of Grand Union main line and the Paddington Arm
3039 | Lock 6, Kidderminster Lock, Staffordshire & Worcestershire Canal | West Midlands | Staffordshire & Worcestershire Canal | Gate replacement works | 04-01-2016 | 12-02-2016 | Broad Waters turning point | Brintons Basin Bridge turning point
3043 | Lock 9, Debdale Lock, Staffordshire & Worcestershire Canal | West Midlands | Staffordshire & Worcestershire Canal | Gate replacement works | 15-02-2016 | 11-03-2016 | Cookley Forge Basin Bridge turning point | Turning point at Worlds End, Lea Lane
3047 | Lock 1, Top Lock, Leigh Branch | North-West | Leigh Branch (Leeds & Liverpool Canal) | Gate replacement works | 02-11-2015 | 30-11-2015 | Leeds & Liverpool Junction | Ince Moss turning point
3051 | Lock 75, Leeds & Liverpool Canal | North-West | Leeds & Liverpool Canal | Gate replacement works. | 15-02-2016 | 11-03-2016 | Haigh Park Rowing bridge | Leigh Branch Junction
3059 | Lock 57 Bottom Lock, Leeds & Liverpool Canal | North-West | Leeds & Liverpool Canal | Gate replacement works and replacement of lock ladder | 15-02-2016 | 11-03-2016 | Eanam Bridge turning point | Bower house fold Bridge turning point
3061 | Lock 52, Top Lock, Leeds & Liverpool Canal | North-West | Leeds & Liverpool Canal | Gate replacement works. | 11-01-2016 | 08-02-2016 | Eanam Bridge turning point | Bower house fold bridge turning point
3063 | Lock 47, Car Park, Leeds & Liverpool Canal | North-West | Leeds & Liverpool Canal | Lock ladder and gate replacement works. | 18-01-2016 | 11-03-2016 | Wanless Bridge turning point | Hodge Bank turning point
3065 | Lock 30, Holme Bridge Lock, Leeds & Liverpool Canal | North-West | Leeds & Liverpool Canal | Gate replacement works. | 02-11-2015 | 23-11-2015 | Winding Hole, Gargrave | Winding Hole - Holme Bridge
3067 | Lock 24, Bingley 3 Rise Top Lock, Leeds & Liverpool Canal | North-West | Leeds & Liverpool Canal | Gate replacement works. | 30-11-2015 | 18-12-2015 | Winding Hole - Bingley Five Rise | Turning Area - Bingley Three Rise
3071 | Lock 2, Salterhebble Middle, Calder & Hebble Navigation | North-East | Calder & Hebble Navigation | Gate replacement works. | 02-11-2015 | 30-11-2015 | Halifax Branch (Calder & Hebble) Junction | Winding Hole downstream Woodside Lock
3075 | Calf Heath Aqueduct | West Midlands | Staffordshire & Worcestershire Canal | Our engineers will undertaking a Principal Inspection of Calf Heath Aqueduct which will include leak investigation works. | 02-11-2015 | 21-11-2015 | 80m from Bridge 72, Slade Heath Bridge. | Before Calf Heath Marina Bridge.
3077 | Lock 2012, Three Mills Lock | London | Prescott Channel | Our engineers will undertaking a Principal Inspection of Three Mills Lock where stop planks will be installed and the lock chamber dewatered. | 16-11-2015 | 20-11-2015 | Before Three Mills Lock. | Before Three Mills Lock.
3079 | Lock 41 | West Midlands | South Stratford Canal | Our engineers will undertaking a Principal Inspection of Lock 41 where stop planks will be installed and the lock chamber dewatered. | 10-11-2015 | 10-11-2015 | 300m from Bridge 59, Featherbed Lane. | Before Lock 44.
3081 | Lock 49 to Lock 55 South Stratford Canal | West Midlands | South Stratford Canal | Our engineers will undertaking a Principal Inspection of Lock 49 where stop planks will be installed and the lock chamber dewatered. In addition to this inspection top & bottom gate repairs and chamber masonry repairs will be undertaken at Lock 55 | 09-11-2015 | 20-12-2015 | Turning Point, north of Bridge 59 | Stratford Basin
3083 | Lock 1, Parkhead Top Lock, Dudley No 1 Canal | West Midlands | Dudley No 1 Canal | Gate replacement works | 09-11-2015 | 18-12-2015 | Parkhead Top Lock, winding hole | Winding hole, Blowers Green
3085 | Lock 7, Park Nook, Calder & Hebble Navigation | North-East | Calder & Hebble Navigation | Gate replacement works. | 16-11-2015 | 14-12-2015 | Winding Hole downstream Woodside Dock | Huddersfield Broad Canal Junction
3087 | Lock 16, Cooper Bridge, Calder & Hebble Navigation | North-East | Calder & Hebble Navigation | Gate replacement works. | 11-01-2016 | 01-02-2016 | Huddersfield Broad Canal Junction | Dewsbury Arm (Calder & Hebble Navigation) junction
3089 | Lock 23, Figure Of Three, Calder & Hebble Navigation | North-East | Calder & Hebble Navigation | Gate replacement works. | 08-02-2016 | 29-02-2016 | Dewsbury Arm (Calder & Hebble Navigation) junction | Wakefield Branch (Aire & Calder Navigation) junction
3091 | Lock 28, Fall Ing, Calder & Hebble Navigation | North-East | Calder & Hebble Navigation | Gate replacement works. | 22-02-2016 | 11-03-2016 | Dewsbury Arm (Calder & Hebble Navigation) junction | Wakefield Branch (Aire & Calder navigation) junction
3093 | Rotton Park, Birmingham Main Line | West Midlands | New Mainline | Our contratcors will be draining a section of canal to allow the reconstruction of a failed waterway wall. Alternative route available around Icknield Port Loop. | 02-11-2015 | 18-12-2015 | Icknield Square Junction Bridge | Rotton Par Junction Bridge
3095 | Tinsley No.2 Lock, Sheffield & Tinsley Canal | North-East | Sheffield & Tinsley Canal | Gate replacement works. | 11-01-2016 | 11-03-2016 | Sheffield Basin turning point | Dearne & Dove Canal junction
3097 | Tinsley No.10 (Wharf Road) Lock, Sheffield & Tinsley Canal | North-East | Sheffield & Tinsley Canal | Gate replacement works. | 11-01-2016 | 11-03-2016 | Sheffield Basin turning point | Dearne & Dove Canal junction
3099 | Izon Turnover bridge, Wednesbury Old Canal | West Midlands | Wednesbury Old Canal | Our contrators will be carrying out, replacement of the bridge deck, steel repairs and repainting the structure. | 04-01-2016 | 11-03-2016 | Ryder's Green Junction | Pudding Green Junction
3101 | Tinsley No.11 Lock, Sheffield & Tinsley canal | North-East | Sheffield & Tinsley Canal | Gate replacement works. | 11-01-2016 | 11-03-2016 | Sheffield Basin turning point | Dearne & Dove Canal Junction
3103 | Bridge1, Walker bridge, Calder & Hebble Navigation | North-East | Calder & Hebble Navigation | Works to repair leakage and failing waterway wall. | 04-01-2016 | 11-03-2016 | Sowerby Bridge basin | Between Bridges 3 and 4
3105 | Rotherham Lock, Sheffield & South Yorkshire Navigations | North-East | Sheffield & South Yorkshire Navigations | Gate replacement works. | 02-11-2015 | 14-12-2015 | Sheffield Basin Turning point | Dearne & Dove Canal Junction
3107 | Bridge 41, Horbury Road, Calder & Hebble Navigation | North-East | Calder & Hebble Navigation | Works to repair a culvert. Works will be carried out by divers in the water. | 04-01-2016 | 04-03-2016 | Dewsbury Arm, below Lock21 | Above Lock 26, Broad Cut Low Lock
3109 | Lock 28, Lowsonford, South Stratford Canal | West Midlands | South Stratford Canal | Gate replacement works | 09-11-2015 | 18-12-2015 | Kingswood Arm turning point | Turning point, north Bridge 59, Featherbed Lane
3111 | Red Doles Lock Bridge 2 | North-East | Huddersfield Broad Canal | Third party contractors will be refurbishing the pipeline that crosses adjacent to the bridge. The canal will remain in water. | 01-02-2016 | 15-02-2016 | Aspley Basin | Downstream of Lock 1- Cooper Bridge
3113 | Lock 63, Clear Water Lock - Towpath Side, Trent & Mersey Canal | Manchester and Pennine | Trent & Mersey Canal | Top gate replacement and the reconstruction of the lock chamber wall. | 02-11-2015 | 24-12-2015
3115 | Roving Bridge, Grand Union Canal | South-East | Grand Union Canal | Works to carry out, steelwork repairs and repainting | 15-02-2016 | 11-03-2016 | Junction of Grand Union main line and the Slough arm | Junction of Grand Union main line and the Paddington Arm
3117 | Hill House Lane Bridge 8 (Learoyd Bridge), Huddersfield Broad canal | North-East | Huddersfield Broad Canal | Third party contractors will be refurbishing the pipeline that crosses adjacent to the bridge. The canal will remain in water. | 01-02-2016 | 15-02-2016 | Aspley Basin | Downstream of Lock 1 - Cooper Bridge
3119 | Brayton Bridge, Selby, Pipe bridge | North-East | Selby Canal | Third party contractors will be refurbishing the pipeline that crosses adjacent to the bridge. The canal will remain in water. | 15-02-2016 | 28-02-2016 | Upstream of Haddlesey Flood Lock in the River Aire | Immmediately upstream of Selby Lock
3123 | Railway Bridge109A adjacent to Accrington Golf Club, Leeds & Liverpool Canal | North-West | Leeds & Liverpool Canal | Network Rail will be replacing the railway bridge and propose to block off the canal and towpath to facilitate the works. A large crane will be sited within the canal. The canal will be completely closed and dewatered. | 02-11-2015 | 05-02-2016 | Between Bridge111D Simpsons Bridge and Bridge 112 Church Kirk Cahangeline Bridge | Between Bridge 109, New Barn Bridge and Bridge 108A Rishton Bridge
3125 | Bethills Bridge pipe crossing | North Wales and Borders | Llangollen Canal | Severn Trent Water will be carrying out refurbishment works to their pipe bridge. | 02-11-2015 | 16-11-2015 | Between Bridges 22 and 23 | Between Bridges 10 and 11
3127 | Horse Close Bridge, Leeds & Liverpool Canal | North-West | Leeds & Liverpool Canal | Third party contractors will be installing a new fixed bridge over the canal The canal will remain in water. | 26-01-2016 | 29-01-2016 | Springs Branch Junction | Downstream of Bridge 183A Farnhill Bridge
3129 | Wrenbury, Bridge 18 and 22, Masonry repairs | North Wales and Borders | Llangollen Canal | Our contractors will be carrying out below water brickwork repairs with fender installation, to bridges 18 (Starkeys Bridge) and bridge 22 (Thomasons Bridge) | 02-11-2015 | 18-12-2015 | Between Bridge 10 and 11 (max 50ft) | Between Bridges 22 and 23
3131 | Gorsey Lane Bridge highway bridge 4A, Leeds & Liverpool Canal | North-West | Leeds & Liverpool Canal | Third party contractors will be refurbishing the bridge. The canal will remain in water. | 02-11-2015 | 18-12-2015 | Near Bridge 9, Hancocks Swingbridge | 730m downstream of Gorsey Lane Bridge 4A
3133 | Danson's Bridge, Bridge 30 | North Wales and Borders | Llangollen Canal | Our contractors will be carrying out belwo water brickwork repairs and fender installation to Danson's bridge. | 02-11-2015 | 18-12-2015 | Between Bridges 30A and 31 | Grindley Brook Locks, Between Locks 3 and 4, Below bridge 29
3135 | Wellington Road Bridge, Leeds | North-West | Leeds & Liverpool Canal | Third party contractors will be installing pipework onto the bridge. The canal will remain in water. | 02-11-2015 | 13-11-2015 | Downstream of Redcote Bridge | Between River Lock and Office Lock
3137 | Pryshenlle Bridge 15W | North Wales and Borders | Llangollen Canal | Our contractors will be carrying out below water brickwork repairs and fender installation. | 02-11-2015 | 18-12-2015 | Between Bridges 18w and19w | Between Bridges 6w and 7w
3141 | Leeds Bridge to Thwaite Mill Bridge | North-East | Aire & Calder Navigation Main Line | Leeds Cty Council are undertaking major works as part of the Leeds Flood Alleviation Scheme. Exact locations of stoppages are to be determined over the length indicated.An update will be published when information is confirmed. This is the 4th of six stoppages for the scheme which is due to finish in March 2016. | 02-11-2015 | 30-11-2015 | In river Aire | At Thwaite Mill Bridge
3143 | Leeds Bridge to Thwaite Mill Bridge | North-East | Aire & Calder Navigation Main Line | Leeds Cty Council are undertaking major works as part of the Leeds Flood Alleviation Scheme. Exact locations of stoppages are to be determined over the length indicated.An update will be published when information is confirmed. This is the 5th of six stoppages for the scheme which is due to finish in March 2016. | 04-01-2016 | 31-01-2016 | In River Aire | At Thwaite Mill Bridge
3145 | Leeds Bridge to Thwaite Mill Bridge | North-East | Aire & Calder Navigation Main Line | Leeds Cty Council are undertaking major works as part of the Leeds Flood Alleviation Scheme. Exact locations of stoppages are to be determined over the length indicated.An update will be published when information is confirmed. This is the sixth of six stoppages for the scheme which is due to finish in March 2016. | 01-03-2016 | 31-03-2016 | In River Aire | At Thwaite Mill Bridge
3147 | Niffany Swing Bridge | North-West | Leeds & Liverpool Canal | Replacement of existing bridge. | 11-01-2016 | 11-03-2016 | Junction with Springs Branch, between Bridges 177 and 178 | Between Bridges 174A and 175
3149 | Leaches Swing Bridge | North-West | Leeds & Liverpool Canal | Repairs to swing bridge | 09-02-2016 | 11-03-2016 | Between Bridges 196 and 197 | Between Bridges 194 and 195
3151 | Dock Lane Swing Bridge (209) | North-West | Leeds & Liverpool Canal | Refurbishment and mechanisation of existing swing bridge | 04-01-2016 | 11-03-2016 | Between Bridges 210 and 211 | Between Bridges 208 and 209
3153 | Calverley Embankment | North-West | Leeds & Liverpool Canal | Works to replace existing culvert and repairs to waterway retaining walls. | 02-11-2015 | 18-12-2015 | Between Bridges 224 and 225 | Apperley Marina East of Bridge 214
3155 | Lock 4, Macclesfield Canal | Manchester and Pennine | Macclesfield Canal | Polyurethane resin injection to resolve leakage | 08-02-2016 | 11-03-2016 | Between Bridges 49A and 50 | Between Bridges 63 and 64
3157 | Knowsley Bridge (95), Macclefield Canal | Manchester and Pennine | Macclesfield Canal | Works to carry out repairs and repainting. | 08-02-2016 | 11-03-2016 | Between Bridges 86 and 87 | Kidsgrove junction with Trent & Mersey Canal
3159 | Goytre Aqueduct | South Wales and Severn | Monmouthshire & Brecon Canal | Works to include: Relining aqueduct, sealing up culverts, relining culvert and construction of new weir and stop plank installation | 09-11-2015 | 12-02-2016 | Between Bridges 78 and 79 | Between Bridges 73 and 74
3161 | Llangynidr, Mon & Brec | South Wales and Severn | Monmouthshire & Brecon Canal | Works to reline length of canal between Bridge 131 and Bridge 132, as well as lock gate refits and chamber brickwrok repairs | 02-11-2015 | 11-03-2016 | Between Bridges 142 and Bridge 143, White Hart Bridge | Between Bridges 127, Old House Bridge and Bridge 126, Aberhowie Bridge
3163 | Marple Flight, Peak Forest Canal | Manchester and Pennine | Peak Forest Canal | Polyurethane resin injection to resolve leakage at Locks 6,14 & 15. Leakage repairs at locks 5, & 16. | 05-01-2016 | 12-02-2016 | Marple, junction with Maccelsfield Canal | Between Marple aqueduct and bridge 17
3165 | Peak Forest Canal Culvert 16 | Manchester and Pennine | Peak Forest Canal | Works to carry out canal bed and culvert repairs | 04-01-2016 | 26-02-2016 | Between Bridges 27 and 28 | Between Bridges 21 and 22
3167 | Rochdale Canal Lock 13 | Manchester and Pennine | Rochdale Canal | Works to repair leakage from lock. | 04-01-2016 | 26-02-2016 | Between Bridges 23 and 24 | Below Lock 12
3169 | Lock3, Minshull, Shrposhire Union Canal | North Wales and Borders | Middlewich Branch (Shrop Union Canal) | Polyurethane resin injection to resolve leakage | 23-11-2015 | 11-12-2015 | Between Bridges 4 and 5 | Church Minshull Marina, East of bridge 8
3171 | Lock 14, Brick Lock | London | River Stort | Brickwork repairs to lock chamber wall. | 11-01-2016 | 09-03-2016 | Marina Entrance Between Bridges 17 and 18 | Marina entrance below lock 2
3173 | Lock 46, Barrowford, Leeds & Liverpool Canal | North-West | Leeds & Liverpool Canal | Gate replacement works. | 11-01-2016 | 08-02-2016 | Wanless Bridge Turning point | Hodge Bank Turning point
3175 | Lock 63, Clear Water Lock - Offside, Trent & Mersey Canal | Manchester and Pennine | Trent & Mersey Canal | Top and bottom gate replacement and lock chamber stabilisation works | 02-11-2015 | 24-12-2015
3177 | Lock 48, Bottom Lock - Towpath Side, Trent & Mersey Canal | Manchester and Pennine | Trent & Mersey Canal | Gate replacement. There will be restriction due to the use of floating plant. | 02-11-2015 | 18-12-2015
3181 | Lock 5, Curdworth, Birmingham & Fazeley Canal | West Midlands | Birmingham & Fazeley Canal | Gate replacement programme | 22-02-2016 | 11-03-2016 | Winding hole, Curdworth Top Lock | Winding hole, Curdworth Bottom Lock
3183 | Lock 10w, Huddersfield Narrow Canal | Manchester and Pennine | Huddersfield Narrow Canal | gate replacement works. | 02-11-2015 | 18-12-2015 | Winding hole - Manns Wharf | Lock 7W turning point
3185 | Lock 2, Saltley, Birmingham & Warwick Junction Canal | West Midlands | Birmingham & Warwick Junction Canal | Gate replacement works | 09-11-2015 | 18-12-2015 | Grand Union Canal junction | Birmingham & Fazeley Canal junction
3187 | Lock 11w, Huddersfield Narrow Canal | Manchester and Pennine | Huddersfield Narrow Canal | Gate replacement works. | 02-11-2015 | 18-12-2015 | Winding hole - Manns Wharf | Lock 7W turning point
3189 | Lock 1, Perry Barr Top Lock, Tame Valley Canal | West Midlands | Tame Valley Canal | Gate replacement works | 04-01-2016 | 05-02-2016 | Rushall Canal junction | Birmingham & Fazeley Canal junction
3191 | Huddersfield Narrow Canal, East. | Manchester and Pennine | Huddersfield Narrow Canal | Works including: Polyurethane resin injection to resolve leakage, at locks 15,18, 19 and 38. Gate replacement works at lock 24 and leakage repairs at lock 8. | 02-11-2015 | 18-12-2015 | Tunnel end Standedge | Aspley Basin, between Bridges 4 and 5
3193 | Farmers Bridge Lock 11, Birmingham & Fazeley Canal | West Midlands | Birmingham & Fazeley Canal | Gate replacement works | 04-01-2016 | 19-02-2016 | New Mainline junction | Winding Hole, Aston junction
3195 | Lock 7, Macclesfield Canal | Manchester and Pennine | Macclesfield Canal | Gate replacement works. | 08-02-2016 | 11-03-2016 | Oakgrove Turning point | Winding Hole 200m West of Bridge 63
3201 | Lock 1, Top Lock, Wolverhampton, Old Main Line | West Midlands | Old Main Line | Gate replacement works | 09-11-2015 | 11-12-2015 | Carvers Arm winding hole, Broad Street | Staffordshire & Worcestershire Canal junction
3203 | Tyrley Lock 1, Tyrley Top Lock, Shropshire Union Canal | North Wales and Borders | Shropshire Union Canal | Gate replacement works. | 04-01-2016 | 05-02-2016 | Tyrley Wharf Turning Point | Market Drayton Turning Point
3205 | Lock 6, Stenson Lock, Trent & Mersey Canal | Central Shires | Trent & Mersey Canal | Gate replacement works | 02-11-2015 | 20-12-2015 | Winding hole, Willington | Winding Hole, Sarson's Bridge
3209 | Lock 13, Cheddleton Top Lock | Central Shires | Caldon Canal | Gate replacement works | 01-02-2016 | 26-02-2016 | Winding Hole, Cheddleton | Winding Hole, Oakmeadowford
3211 | Lock 21 Worcester & Birmingham Canal | South Wales and Severn | Worcester & Birmingham Canal. | Gate and Lock ladder replacement | 05-01-2016 | 18-01-2016 | Downstream of Bridge 60, Alvechurch - Scarfield Wharf | Between Lock 18 and Lock
3213 | Lock 14, Cheddleton Bottom Lock, Caldon Canal | Central Shires | Caldon Canal | Gate replacement works | 01-02-2016 | 26-02-2016 | Winding Hole, Cheddleton | Winding Hole, Oakmeadowford
3215 | Lock 7, Railway Lock, Caldon Canal | Central Shires | Caldon Canal | Gate replacement works | 04-01-2016 | 29-01-2016 | Winding Hole, Hazelhurst | Winding Hole, Foxley
3217 | Milworth Lock | West Midlands | Birmingham & Fazeley Canal | Lock Ladder replacement | 04-01-2016 | 11-03-2016 | Salford Junction | Between Wiggins Hill Bridge and Minworth Green Bridge
3219 | Lock 36, Stoke Bottom Lock, Trent & Mersey Canal | Central Shires | Trent & Mersey Canal | Gate replacement works | 23-11-2015 | 18-12-2015 | Caldon Canal junction | Winding Hole, Glebe Street
3221 | Audlem Lock Flight | North Wales and Borders | Shropshire Union Canal | Lock Gate replacement at Lock 6 and lock ladder replacement at locks 14,12,10,9,8&7 | 04-01-2016 | 11-03-2016 | Upstream Bridge 69 Adderley Wharf Bridge | Downstream of Bridge 79 Moss Hall
3223 | Trent & Mersey, Marbury and Marton | Manchester and Pennine | Trent & Mersey Canal | Repairs to Marbury Weir crest and bickwork repairs to Bridge 193, Ollershaw Lane brige. | 16-11-2015 | 23-12-2015 | Marina entrance near bridge 198, Common Turn Bridge | Between bridge 191 and bridge 189
3225 | Lock 53, Loughborough Lock, River Soar | Central Shires | River Soar | Gate replacement works | 04-01-2016 | 11-03-2016 | Winding Hole, Pillings | Upper Trent junction
3227 | Lock 50, Mountsorrel Lock, River Soar | Central Shires | River Soar | Gate replacement works | 04-01-2016 | 11-03-2016 | Winding Hole, near Bridge 98 (Glen Parva) | Winding Hole, Pillings
3229 | Lock 41, Freemans Meadow Lock, Leicester Line (Grand Union Canal) | Central Shires | Leicester Line (Grand Union Canal) | Gate replacement works | 04-01-2016 | 11-03-2016 | Winding Hole, near Bridge 98 (Glen Parva) | Winding Hole, Pillings
3231 | Lock 2, Diglis, Worcester & Birmingham Canal | South Wales and Severn | Worcester & Birmingham Canal. | Gate replacement works | 02-11-2015 | 13-11-2015 | Diglis Basin turning point | River Severn Navigation turning point
3233 | Lock 8, Bilford, Worcester & Birmingham Canal | South Wales and Severn | Worcester & Birmingham Canal. | Gate replacement works | 16-11-2015 | 27-11-2015 | Winding Hole, Tibberton | Winding Hole, Bilford
3235 | Lock 10, Tolladine, Worcester & Birmingham Canal | South Wales and Severn | Worcester & Birmingham Canal. | Gate replacement works | 30-11-2015 | 18-12-2015 | Winding Hole, Tibberton | Winding Hole, Bilford
3237 | Lock 23, Worcester & Birmingham Canal | South Wales and Severn | Worcester & Birmingham Canal. | Gate replacement works | 19-01-2016 | 15-02-2016 | Winding Hole, near Alvechurch Station, Newbourne Hill | Winding Hole, Astwood Lane, Astwood
3239 | Lock 32, Worcester & Birmingham Canal | South Wales and Severn | Worcester & Birmingham Canal. | Gate replacement works | 08-02-2016 | 19-02-2016 | Winding Hole, near Alvechurch Station, Newbourne Hill | Winding Hole, Astwood Lane, Astwood
3241 | Lock 41, Worcester & Birmingham Canal | South Wales and Severn | Worcester & Birmingham Canal. | Gate replacement works | 23-01-2016 | 11-03-2016 | Winding Hole, near Alvechurch Station, Newbourne Hill | Winding Hole, Astwood Lane, Astwood
3243 | Lock 10, Aylesbury Arm (Grand Union Canal) | South-East | Aylesbury Arm (Grand Union Canal) | Gate replacement works | 02-11-2015 | 20-11-2015 | Grand Union Canal junction | Winding Hole, Red House
3245 | Lock 12, Shop Lock, Grand Union Canal | South-East | Grand Union Canal | Gate and Lock ladder replacement | 11-01-2016 | 29-01-2016 | Bridge 17 Napton Junction | Between Bridge 34 Butt Lane and Bridge 35 Radford Road
3247 | Lock 6, 10, and 11 Northampton Arm (Grand Union Canal) | South-East | Northampton Arm (Grand Union Canal) | Gate replacement works plus various associated repairs | 04-01-2016 | 28-02-2016 | Winding Hole, near Milton Malsor | Winding Hole, Northampton Bottom Lock 17
3249 | Lock 14, 15, and 17 Northampton Arm (Grand Union Canal) | South-East | Northampton Arm (Grand Union Canal) | Gate replacement works and other associated repairs | 04-01-2016 | 28-02-2016 | Winding Hole, near Milton Malsor | Winding Hole, Northampton Bottom Lock 17
3251 | Lock 10, Grand Union Canal | South-East | Grand Union Canal | Gate replacement works | 02-11-2015 | 20-12-2015 | Norton Junction, Leicester Line (Grand Union Canal) junction | Winding Hole, between Locks 12-13
3253 | Lock 11, Grand Union Canal | South-East | Grand Union Canal | Gate replacement works | 02-11-2015 | 20-12-2015 | Norton Junction, Leicester Line (Grand Union Canal) junction | Winding Hole, between Locks 12-13
3255 | Lock 12, Grand Union Canal | South-East | Grand Union Canal | Gate replacement works | 02-11-2015 | 18-12-2015 | Norton Junction, Leicester Line (Grand Union Canal) junction | Winding Hole, between Locks 12-13
3257 | Lock 69A, Kings Langley, Grand Union Canal | South-East | Grand Union Canal | Gate replacement works | 11-01-2016 | 29-01-2016 | Winding Hole, Winkwell | Turning Point, Grove Wharf
3261 | Ashton Canal | Manchester and Pennine | Ashton Canal | Flight closure for repairs to brickwork, heel grips and leakage reduction. | 04-01-2016 | 11-03-2016 | Above Lock 18, Droylsden Basin | Bridge 1, Junction with Rochdale Canal
3265 | Lock 82, Stockers Lock, Grand Union Canal | South-East | Grand Union Canal | Gate replacement works | 08-02-2016 | 26-02-2016 | River Chess junction | Slough Arm (Grand Union Canal) junction
3267 | Lock 3, Standards Lock, Bridgwater & Taunton Canal | Kennet and Avon | Bridgwater & Taunton Canal | Gate replacement works | 02-11-2015 | 18-12-2015 | Winding Hole, near Maunsel Higher Bridge | Winding Hole, Bridgwater
3269 | Lock 104, Southcote Lock, Kennet & Avon Canal | Kennet and Avon | Kennet & Avon Canal | Gate replacement works | 02-11-2015 | 20-12-2015 | Southcote Moorings (Kennet & Avon Canal) junction | River Thames junction
3271 | Foxhangers Locks, Kennet & Avon Canal | Kennet and Avon | Kennet & Avon Canal | Leakage reapirs at locks 23 and 24 | 04-01-2016 | 11-03-2016 | Devizes Wharf, 72 Foot Winding Hole | Whaddon, 65 Foot Winding Hole
3273 | Lock 21, Seend Lock, Kennet & Avon Canal | Kennet and Avon | Kennet & Avon Canal | Gate replacement works | 04-01-2016 | 11-03-2016 | Devizes Wharf, 72 Foot Winding Hole | Whaddon, 65 Foot Winding Hole
3275 | Lock 3, Kentish Town Lock, Regents Canal | London | Regent's Canal | Gate replacement works | 04-01-2016 | 11-03-2016 | Cumberland Basin, Prince Albert Road | Below Lock 4, St Pancras lock winding hole
3277 | Lock 10, Johnsons Lock, Regent's Canal | London | Regent's Canal | Gate replacement works | 02-11-2015 | 18-12-2015 | Hertford Union Canal junction | Limehouse Basin, Limehouse Cut
3279 | Lock 9, Latton Lock, River Stort | London | River Stort | Gate replacement works | 02-11-2015 | 18-12-2015 | Adderley Road turning point, Bishop's Stortford | Lee Navigation junction
3281 | Huddersfield Narrow Canal, West | Manchester and Pennine | Huddersfield Narrow Canal | Works including: Polyurethane resin injection to resolve leakage at Lock 24w, Waterway wall, brickwork and leakage reapirs at locks 22,23 and 28. | 09-11-2015 | 18-12-2015 | Above lock 32 west | Manns Wharf, between Bridges 81 and 82
3285 | Baddiley Locks | North Wales and Borders | Llangollen Canal | Works to carry out brickwork, leakage and timber repairs. | 02-11-2015 | 20-11-2015 | Between Bridges 22 and 23 | Between Bridges 10 and 11
3289 | Bridge 45W, Llangollen Canal | North Wales and Borders | Llangollen Canal | Works to carry out leakage and masonry repairs. | 05-01-2016 | 29-01-2016 | Llangollen Basin between bridges 45w and 46w | Trevor Basin near bridge 31w
3291 | Lock 50 & 51 Leeds Liverpool Canal | North-West | Leeds & Liverpool Canal | Polyurethane resin injection to resolve leakage. | 04-01-2016 | 28-02-2016 | Between Bridges 145 and 144 | Between Bridge 141D and 141C
3293 | Captains Clarks Bridge, Peak Forest Canal | Manchester and Pennine | Peak Forest Canal | Works to carry out masonry repairs to bridge above and below waterline. | 01-02-2016 | 19-02-2016 | Between Bridges 10 and 11 | Between Bridges 5A and 6
3295 | South Stratford Canal, Lapworth Flight | West Midlands | South Stratford Canal | Grouting and brickwork repairs to lock chambers at locks 21 and 24 to 27. | 02-11-2015 | 18-12-2015 | Lapworth Junction | Between Bridges 58 and 59
3297 | Lock 10, Wharton's Lock. Shropshire Union Canal | North Wales and Borders | Shropshire Union Canal | Buffer installation to bottom gate of lock. | 04-01-2016 | 15-01-2016 | Between Bridges 107 and 108 | Between Bridges 108 and 109
3301 | Adderley Locks 4 &5 | North Wales and Borders | Shropshire Union Canal | Lock gate leakage repairs. | 25-01-2016 | 11-03-2016 | Upstream Bridge 69, Adderley Wharf Bridge | Downstream of Bridge 79, Moss Hall
3305 | Bridge 22, Bully's Bridge. Trent & Mersey Canal | Central Shires | Trent & Mersey Canal | Steel work repairs and re-painting | 02-11-2015 | 18-12-2015 | Merci Marina entrance, between bridges 22 and 23 | Stenson Marina entrance, between bridges 19 and 20
3307 | Worcester & Birmingham Locks 23 to 26 | South Wales and Severn | Worcester & Birmingham Canal. | Brickwork repairs in lock chambers. | 04-01-2016 | 11-03-2016 | Downstream of Bridge 60, Alvechurch - Scarfield Wharf | Between Lock 18 and Lock 19
3311 | Marsh Lock, Weaver Navigation | North Wales and Borders | Weaver Navigation | Dredging and inspection of lock chamber. | 04-01-2016 | 11-03-2016
3313 | Woodseaves Cutting, Shropshire Union Canal | North Wales and Borders | Shropshire Union Canal | Cutting stabilisation works. | 08-02-2016 | 11-03-2016 | Goldstone Wharf, near bridge 55 | Tyrley Wharf between bridges 59 and 60
3315 | Anderton Boat Lift | North Wales and Borders | Weaver Navigation | Works include; Principal inspection of the boat lift and repairs and maintenance of the hydraulic systems. | 02-11-2015 | 18-12-2015
3315 | Anderton Boat Lift | North Wales and Borders | Trent & Mersey Canal | Works include; Principal inspection of the boat lift and repairs and maintenance of the hydraulic systems. | 02-11-2015 | 18-12-2015 | Marina entrance between bridges 198 and 197 | Between Bridges 206 and 207
3317 | Lock 47, Top Lock - Towpath Side, Trent & Mersey Canal | Manchester and Pennine | Trent & Mersey Canal | Gate replacement works | 02-11-2015 | 18-12-2015 | Between Locks 49 and 50 | Above lock 41 Junction With Macc
3319 | Stamp End Lock | East Midlands | River Witham | Investigation works | 02-11-2015 | 18-12-2015 | Brayford pool basin
3323 | West India Dock Entrance | London | South Dock | Stoppage to carry out repairs to outer gate pintel. | 04-01-2016 | 11-03-2016
3325 | Regent's Canal, Mile End | London | Regent's Canal | Repairs to waterway wall to prevent failure. | 02-11-2015 | 21-12-2015 | Kingland Basin | Limehouse Basin
3327 | Worcester & Birmingham Lock 4 to 6 | South Wales and Severn | Worcester & Birmingham Canal. | Masonry repairs to the lock chambers. | 02-11-2015 | 18-12-2015 | Between Lock 7 and Lock 8 | Diglis Basin, between lock 2 and Bridge 2
3329 | Nottingham | East Midlands | Nottingham & Beeston Canal | Construction of a new bridge by a third party developer | 01-02-2016 | 14-02-2016 | Castle Marina entrance | Just below Beeston Lock
3335 | Bridge No. 103 Navigation | South Wales and Severn | Monmouthshire & Brecon Canal | This stoppage relates to the construction of the A465 dualling scheme in the Gilwern area. The works include site clearance of existing vegetation from the southern canal bank, and the construction of retaining walls to support the new highway and slip road at this location. | 02-11-2015 | 20-12-2015 | Winding Hole Dan-Y-Graig Bridge 107 (25m from Bridge 107, Dan-Y-Graig). | Winding Hole Heads of the Valley (200m from Bridge 102, Ty-Gwynn).
3337 | Preston Brook Tunnel, Trent & Mersey Canal | Manchester and Pennine | Trent & Mersey Canal | Inspection team will be blocking the tunnel with a workboat for a period of 8 hours to undertake a Principal Inspection. | 17-11-2015 | 17-11-2015 | south of tunnel | Bridgewater Canal Junction
3339 | Saltersford Tunnel, Trent & Mersey Canal | Manchester and Pennine | Trent & Mersey Canal | Inspection team will be blocking the tunnel with a workboat for a period of 2 days to undertake a Principal Inspection. | 23-11-2015 | 24-11-2015 | Eastern portal | downstream of Bradley Meadow Bridge 206
3341 | Barnton Tunnel, Trent & Mersey Canal | Manchester and Pennine | Trent & Mersey Canal | Inspection team will be blocking the tunnel with a workboat for a period of 3 days to undertake a Principal Inspection. | 25-11-2015 | 27-11-2015 | eastern portal | western portal
3343 | Drakeholes Tunnel, Chesterfield Canal | East Midlands | Chesterfield Canal | Inspection team will be blocking the tunnel with a workboat for a period of 4 hours to undertake a Principal Inspection. | 10-11-2015 | 10-11-2015 | southern portal | downstream of Manor Farm Bridge 78
3391 | Wardle Lock, Middlewich Branch | North Wales and Borders | Middlewich Branch (Shrop Union Canal) | Gate replacement works | 09-11-2015 | 11-12-2015 | Between bridges 16 and 18 | Junction with Trent & Mersey Canal
3907 | Seend Wharf Bridge | Kennet and Avon | Kennet & Avon Canal | Update: The condition of the bridge has further deteriorated and the works required are critical. As a result the planned dates for this stoppage, have had to be changed. This is to allow the construction works to start as early as possible. This also means that the navigation will not be open over the Christmas period as previously planned. Deck strengthening works to bridge. Temporary works beneath bridge will prevent navigation. | 02-11-2015 | 11-03-2016 | Between Bridge 141 Devizes Town and Bridge 140 Cemetery Road | Between Bridge 162 Whaddon Grove Bridge and Bridge 161 Semington Swing Bridge
3915 | Pewsey Embankment, Kennet and Avon | Kennet and Avon | Kennet & Avon Canal | Stabilisation works to embankment and waterway wall repairs. | 09-11-2015 | 18-12-2015 | Milkhouse winding hole, between Bridges 111 and 112 | Alton Valley winding hole, between bridges 123 and 124
3917 | Park Farm Culvert, Culvert 19a | South-East | Leicester Line (Grand Union Canal) | Draining of the canal to allow bed repairs over the line of the culvert. | 11-01-2016 | 11-03-2016 | Winding hole 6, between bridges 34 and 36 | Winding hole 5, between bridges 28 and 29
3919 | Bridge 87 | South-East | Grand Union Canal | To carry out repairs and stabilisation works to a brick arch bridge. Works to bridge and piling operations lead to the requirement of a stoppage rather than a restriction. | 18-01-2016 | 26-02-2016 | Between Bridges 82B and 83 | Between Bridges 98 and 98A
3921 | Bridge 180A - Railway bridge | Manchester and Pennine | Trent & Mersey Canal | Essential maintenance work to bridge by Murphy's contractors on behalf of Network Rail. redecking the bridge, so damger of falling objects. | 02-11-2015 | 18-12-2015 | Middlewich winding hole, between Lock 75, Big Lock and bridge 172 | Broken Cross winding hole, between bridges 183 and 184
3923 | Lock 7, Meadow Lane Lock, Nottingham | East Midlands | Nottingham & Beeston Canal | This stoppage is required whilst repairs are carried out to Turners Quay weir. The lock will be used to control water levels for safety reasons. | 08-02-2016 | 19-02-2016
3947 | Bridge 129A near Burnley | North-West | Leeds & Liverpool Canal | Network Rail will be replacing the railway bridge. The canal will not be dewatered. Further details will be confirmed on receipt. | 23-09-2015 | 23-12-2015 | Between Br 130 Sandygate Bridge & 130B Manchester Road Bridge | Between Bridge 129 Whittlefield Bridge and Gannow Tunnel
3953 | Culvert 38, Llangollen, Llangollen Canal | North Wales and Borders | Llangollen Canal | De-water and repair canal bed and culvert | 09-11-2015 | 11-12-2015 | Bridge 42 Tilstock Park | Bridge 32 & 33
3969 | Lock 49 Morse Lock, Chesterfield Canal | East Midlands | Chesterfield Canal | Paddle Repairs. | 11-01-2016 | 18-01-2016 | Worksop Winding Hole | Sandhill Lake Winding Hole
3973 | Railway Bridge, Consall Forge, Caldon Canal | Central Shires | Caldon Canal | To replace the timber walkway under the Bridge | 04-01-2016 | 26-02-2016 | Winding Hole, Oakmeadowford | Winding Hole, Flintmill Lock
3975 | Lock 36, Otherton Lock, Staffordshire & Worcestershire Canal | West Midlands | Staffordshire & Worcestershire Canal | Top and bottom gate leakage, and masonry repairs | 02-11-2015 | 18-12-2015 | Turning Point next to Calf Heath Bridge | Moat House Winding Hole
3977 | Locks 4, Camp Hill, Lock 55 and Lock 5, Camp Hill. Lock 56, Grand Union Canal | West Midlands | Grand Union Canal | Top and bottom gate repairs, as well as chamber masonry repairs | 04-01-2016 | 11-03-2016 | Moat House Winding Hole | Birmingham & Warwick Junction Canal junction
3979 | Lock 15, Rocky Lock, Staffordshire & Worcestershire Canal | West Midlands | Staffordshire & Worcestershire Canal | Top gate leakage repairs | 09-11-2015 | 15-11-2015 | Bratch Winding Hole | Stourbridge Canal junction
3983 | Locks 32 to 44, Grand Union Canal | West Midlands | Grand Union Canal | Leak repairs to Hatton Flight | 04-01-2016 | 11-03-2016 | Winding Hole, Hatton Station | Winding Hole, Saltisford Junction
3987 | Lock 70, Barkers Lock, Erewash Canal | East Midlands | Erewash Canal | Lock gate replacement. | 02-11-2015 | 14-12-2015 | Botany Bay - Winding Hole | Facility - Winding Hole
3989 | Bridge 155, Court Farm Liftbridge, Monmouthshire & Brecon Canal | South Wales and Severn | Monmouthshire & Brecon Canal | Stop plank cill installation | 02-11-2015 | 20-11-2015 | Winding Hole Storehouse Bridge 158 | Winding Hole Pencelli
3991 | Lock 13, Newark Town Lock, River Trent | East Midlands | River Trent | Gate replanking and various brickwork repairs. | 19-10-2015 | 14-12-2015 | Entrance to Newark Marina | Between Lock 13 and Bridge 22, Trent bridge
3993 | Lock 11, Coventry Canal | West Midlands | Coventry Canal | Gate leakage and masonry repairs | 15-02-2016 | 11-03-2016 | Winding Hole, Atherstone Top Lock | Winding Hole, Grendon
3997 | Lock 12, Coventry Canal | West Midlands | Coventry Canal | Gate leakage and masonry repairs | 18-01-2016 | 14-02-2016 | Winding Hole, Glascote | Winding Hole, Fazeley junction
3999 | Lock 13, Bagnall Lock to Lock 11, Wychnor Lock, Trent & Mersey Canal | Central Shires | Trent & Mersey Canal | Top and bottom gate repairs and associated masonry repairs | 02-11-2015 | 18-12-2015 | Winding Hole, Fradley junction | Winding Hole, Wychnor
4001 | Sheffield Lock 101, Kennet & Avon Canal | Kennet and Avon | Kennet & Avon Canal | Lock chamber stabilisation works | 18-01-2016 | 11-03-2016 | Winding Hole, Tyle Mill 72ft | Winding Hole, Sheffield 35ft
4003 | Locks 6 & 7, Stourbridge | West Midlands | Stourbridge Canal | Top gate leak repairs and cill repairs | 08-02-2016 | 11-03-2016 | Winding Hole, Wordsley | Stourbridge Town Arm junction
4005 | Bridge 37, Kingswood Arm (North Stratford Canal) | West Midlands | Kingswood Arm (North Stratford Canal) | Masonry repairs | 04-01-2016 | 07-02-2016 | South Stratford junction | North Stratford junction
4007 | Lock 14, Lock 15, and Bridge 16, Aylesbury Arm (Grand Union Canal) | South-East | Aylesbury Arm (Grand Union Canal) | Leak related Lock work, and Bridge related brickwork | 02-11-2015 | 02-12-2015 | Winding Hole, Red House | N/A
4009 | Lock 14, Lock 15, and Bridge 16, Aylesbury Arm (Grand Union Canal) | South-East | Aylesbury Arm (Grand Union Canal) | Leak related Lock work, and Bridge related brickwork | 02-11-2015 | 02-12-2015 | Winding Hole, Red House | N/A
4011 | Roundham Lock, Oxford Canal | South-East | Oxford Canal | Gate refit works | 02-11-2015 | 13-11-2015 | Winding Hole 12, Lince Lane | Dukes Cut (Oxford Canal) junction
4013 | Summerton Deep Lock, Oxford | South-East | Oxford Canal | Gate reline works | 16-11-2015 | 27-11-2015 | Winding Hole 9 | Winding Hole, Somerton
4015 | Grants Lock, Oxford Canal | South-East | Oxford Canal | Gate liner works | 30-11-2015 | 07-12-2015 | Winding Hole 7 | Winding Hole 8
4017 | Little Bourton Lock 27, Oxford Canal | South-East | Oxford Canal | Gate liner repairs | 10-12-2015 | 18-12-2015 | Winding Hole 6 | Turning Point, Banbury
4019 | Radford Bottom Lock to Stockton Flight, Grand Union Canal | South-East | Grand Union Canal | Cills, fenders, and reline works | 11-01-2016 | 11-03-2016 | Oxford Canal junction | Winding Hole, Radford Semele
4021 | Stoke Bruerne, Grand Union Canal | South-East | Grand Union Canal | Gate repairs and masonry repairs | 08-02-2016 | 18-03-2016 | Winding Hole, Bilsworth Tunnel (south side) | Winding Hole, Navigation Inn
4023 | Horton Lock to Seabrook Lock, Grand Union Canal | South-East | Grand Union Canal | Gate relining works | 11-01-2016 | 26-02-2016 | Aylesbury Arm junction | Winding Hole, Slapton
4025 | Lock 56, Grand Union Canal | South-East | Grand Union Canal | Gate relining works | 29-02-2016 | 11-03-2016 | Winding Hole, Cow Roast | Winding Hole, Winkwell
4027 | Cassiobury Park Lock 75, Grand Union Canal | South-East | Grand Union Canal | Gate relining works | 07-03-2016 | 09-03-2016 | Turning Point, Grove Wharf | Winding Hole, Common Moor